## Summary
INDEPENDENT REVIEW
Project Title: | MDC Validation Centre of Excellence |  | Scheme Promoter: | Medicine Discovery Catapult
Document Reviewed: | BUSINESS CASE MDC V 1.0 |  | Permission Sought: | Full Approval
Date of Submission: | 2020-11-13 |  | Date of Review: | 2020-11-15
LEP Accountability Framework:
Scheme Description: | The project is seeking capital funding to support the development of a diagnostic, biomarkers and therapeutics testing lab at Alderley Park. The Lab will provide essential testing services to SMEs and academic partners with a view to supporting the development and subsequent commercialisation of new therapeutic treatments for viral pathogens including Covid-19.
SUMMARY SHEET
Overall Score: | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission, project to progress as scheduled.
Overall Comments: | The overall assessment is subject to the caveat that we have not been involved in generating the raw information relating to finance or impacts. We have therefore assumed that this infomation as provided by MDC is accurate. With this in mind, overall, the case for the project is robust in terms both of the potential for economic benefit in the LEP area, and also as part of the national effort to develop the UK's capacity to manage future viral pandemics. It has a strong fit with local and national policy priorities, offers good value of money and with the strong track record of the applicant (MDC) should be relatively low risk. The submission itself falls short of full Green Book compliance in some areas, most notably the options apraisal, economic appraisal and some areas of detail in the Management and Financial Cases. In relation to the Economic Case, a proportionate approach is warranted. Subjecting all options to full economic appraisal is not likely to add to the overall case for investment, nor would it result in a different preferred option. However,the LEP may wish to seek further infomation to verify the in kind support fom Alderley Park and to clarify the economic and financial risks as outlined in the review. Overall, the submission seems suitably robust for a project of this nature and scale. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission. Project to progress and issues to be resolved.
|  |  |  | 3 | Requirements partially met - Medium issues exist with the submission. Project to progress and issues to be resolved urgently.
|  |  |  | 4 | Requirements not met - Critical issues exist with the submission. Project to be suspended whilst issues are resolved.
Case | Status | WSP Comments
Strategic Case | 1 | The Strategic Case appears to be quite strong, even if the evidence base is limited in some places. The Project objectives are clear and there is a strong fit with strategic priorities at national and local levels.
Economic Case | 2 | The Economic Case falls short of full Green Book compliance in terms of both the option appraisal and the extent of the impact assessment. However, there is sufficient detail to demonstrate genuine consideration of alternative options and to evidence value for money within an acceptable BCR range. The argument that the forecast impacts are a likely understimation does have some merit and partly mitigates the lack of optimism bias in the BCR calculations.
Financial Case | 2 | All main elements are covered, but would benefit from more detail regarding third party contributions, and financial risks (even if these do appear manageable).
Commercial Case | 1 | All main elements are covered.
Management Case | 2 | Overall the Management Case seems to be sufficiently robust. Some minor amendments to the risk scoring and some detail on assurance and approvals processes and future stakeholder engagement would be useful.
Sign-Off
Reviewer's Signature: |  |  | Date: | 2020-11-15

## Strategic Case
INDEPENDENT REVIEW
Project Title: |  |  | MDC Validation Centre of Excellence
Permission Sought: |  |  | Full Approval |  | Date of Review: | 2020-11-15
STRATEGIC CASE
Overall Score |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  | The Strategic Case appears to be quite strong, even if the evidence base is limited in some places. The Project objectives are clear and there is a strong fit with strategic priorities at national and local levels. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[6 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[6 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Key relevant sections in Business Case | FBC Status | Comments
S1 | Is there a clear description of the components of the scheme and how it fits with the LEP's Strategic Economic Plan (and LIS) and any other strategic plans e.g. Local Authority and Dft | A5,B1, B3 and B4 | Requirements Fully Met | Space for the project decription is limited on the form but Section B1 provides a clear account of the fit of the project with policies and strategies at national, and local level, including the LEP's Strategic Economic Plan and LIS.
S2 | Have the problem(s) the scheme will be addressing been clearly identified? | B2 and B4 | Requirements Fully Met | Yes. The Covid pandemic has exposed current limitations in the UK's diagnostic and therapeutics testing infrastructure, and the facilities that are available are not generally accessible to SMEs due to the highly sensitive nature of their work and the need for appropriate security. This is a constraint on innovation in this area of the life science sector. The evidence base on the economic value of the sector is quite limited, but the application has highlighted relevent data and evidence where possible.
S3 | Is there a set of specific, measurable, achievable, realistic, time-bound (SMART) objectives for the scheme to address the problem(s) identified? | B3 | Requirements Fully Met | Yes, the objectives are clear and SMART
S4 | Are the expected outcomes clear and how they will be assessed? | B3, C1, C2 and E8 | Requirements Fully Met | Section C1 provides a clear account of the expected outcomes and impacts and how these are to be achieved. Section E8 sets out the monitoring and evaluation plans which appear to be robust and clear.
S5 | Have any interdependencies which may affect the delivery of the scheme been identified? | E3 | Requirements Fully Met | Project dependencies are covered in Section E3 in the Management Case .
S6 | Have relevant studies and technical work that has informed the development of the scheme been identified? | B2, B4 and H2 | Requirements Fully Met | The evidence base is somewhat limited for a number of reasons. First, while similar labs do exist elsewhere, they are typically under academic or government control, and handle highly sensitive projects (e.g. working with pathogens that could present serious national security risks). As a result, they are not easily accessible to the commerical sector and there is little in the way of published information on these facilities. There is also little published data on the diagnostics and therapeutics sector in the region, and what there is has been identified and quoted in the application.Therefore, some of the evidence presented is more anecdotal or based on the experience of MDC and its commercial partners. There is, however, some evidence on the economic scale and performance of the sector, how it has been negatively impacted by the pandemic and on the unmet demand for the diagnostic testing services and facilities that the project will provide. Section H2 also provides useful evidence from government and the Academy of Medical Sciences of the need to improve the UK's diagnostic testing capacity and capabilities both in light of Covid-19 and to support a robust response to future pandemics. Finally, also in Section H2 there is strong evidence to demonstrate the scale of the global opportunity in the diagnostics testing market.
S7 | Have any links with other schemes been articulated and how they benefit each other? | B6 | Requirements Fully Met | Yes, this has been comprehensively addressed and highlights important links to the MDC Strength in Places Fund bid (pending) and the UK Lighthouse Lab, the retention of which in the region is an important side benefit of the project.
S8 | Has there been consultation with stakeholders in the development of the scheme? | E6 and Appendix | Requirements Fully Met | Section E6 details the consultation that has been undertaken with local commerical and academic interests and this has both informed the project and helped to scale likely demand for services. The consultation is supported by Letters of Support contained in the Appendix.
S9 | Is there a robust options appraisal? | C4 | Requirements Partially Met | The Options Appraisal is presented in Section C4 in the Economic Case. The options considered appear sensible in light of the projett objectives. And each is dscribed abdappraised in qualitative terms. While we could not say that the appraisal is fully compliant with HM Treasury Green Book, it does demonstrate sufficient thought as to alternative means of achieving the options and arrives at a highly credible conclusion in favour of the preferred option.
S10 | Have details of stakeholder and public consultation been provided if applicable. | Appendix | Requirements Fully Met | Yes, letters of support have been included. There has been no public consultation.

## Commercial Case
INDEPENDENT REVIEW
Project Title: |  |  | MDC Validation Centre of Excellence
Permission Sought: |  |  | Full Approval |  | Date of Review:
COMMERCIAL CASE
Overall Score |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  | All main elements are covered. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[6 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[6 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Key relevant sections in Business Case | FBC Status | Comments
C1 | Is the procurement strategy set out and the reason for the choice justified? | F1 and F2 | Requirements Fully Met | The procurement strategy is clear and driven by the procurement approach of MDC generally, and notes compliance with all relevant guidance and legislation.
C2 | Have the proposed payment mechanisms been identified? | F4 and F5 | Requirements Substantially Met | Payment mechanisms are not specifically covered but the stuctures for contract management are clearly set out. It should be noted that the form does not specifically request information on payment mechanisms.
C3 | Have the procurement timescales been set out, and are they realistic? | F3 | Requirements Fully Met | Yes. A timetable has been provided and seems reasonable.
C4 | Have details of contract management been provided, including contract timescales? | F4, F5 and F6 | Requirements Fully Met | Yes, contract management arrangements are clear and robust.
C7 | Has evidence of relevant approval been provided from Head of Procurement? |  | Requirements Fully Met

## Management Case
INDEPENDENT REVIEW
Project Title: |  |  | MDC Validation Centre of Excellence
Permission Sought: |  |  | Full Approval |  | Date of Review:
MANAGEMENT CASE
Overall Score |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  | Overall the Management Case seems to be sufficiently robust. Some minor amendments to the risk scoring and some detail on assurance and approvals processes and future stakeholder engagement would be useful. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[6 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[6 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Key relevant sections in Business Case | FBC Status | Comments
M1 | Has the proposed governance / organisational structure been provided? Does it provide a robust means of overseeing project delivery with appropriate skills / experience? | E5 | Requirements Fully Met | Yes. The governance appoach seems to be robust. MDC has an experienced project manager for the capital works and will itself manage the facility once operational. This is well within MDC's area of expertise and there should be no concerns about management capability.
M2 | Does the project programme demonstrate realistic delivery timescales? Does it provide an appropriate level of detail, eg in GANTT chart form? | E2 | Requirements Fully Met | Yes a GANTT chart is provided covering the capital development, and appears realistic. MDC is an experienced scientific organisation, and there is no reason to doubt the robustness of the planning work.
M3 | Have critical path items and dependencies been clearly identified? | E2 and E3 | Requirements Fully Met | Yes, there is a detailed timetable and critical dependencies are identifed.
M4 | Have required statutory powers and consents been identified, including current status and timescales for obtaining these powers if they are not already in place? | n/a | Requirements Partially Met | There is no mention of statutory powers, and it is no clear what would be required in this respect. There is also no mention of any consents, including planning consent, and it may be wise to check what, if anything, is required.
M5 | Have details of the reporting, assurance and approval process been provided? | E5 | Requirements Substantially Met | This is contained within the section on Project Governance, but would benefit from more detail regarding processes as well as structures.
M6 | Has evidence of scheme delivery been provided, to demonstrate that the delivery body has the capability and means to successfully implement the scheme? | E5 | Requirements Fully Met | Yes. MDC's credentials are provided.
M7 | Have key risks been identified and are suitable mitigation measures proposed? | E6 | Requirements Substantially Met | Yes, a full Risk Register is provided which identfies the main areas of risk for the project together with suitable mitigating actions. Some of the scoring may tend towards the optimistic (e.g.in relation to cost overruns, demand shortfall and achieving economic impacts). These could be revised slightly and should be carefully monitored throughout the delivery period.
M8 | Is there a Stakeholder Management Plan that identifies key stakeholders and details how engagement / consultation will be undertaken? | E6 | Requirements Partially Met | The appplication describes the Stakeholder consultation that has already been undertaken and it is clear that MDC has an active and strong network so ongoing consultation should not present any issues. However, some detail should be provided on this.
M9 | Has a Monitoring & Evaluation Plan been provided that identifies proposed data / performance indicators to monitor against the scheme objectives? | E8 | Requirements Fully Met | Yes, the Monitoring and Evaluation Plan seems robust.
M10 | Are there clear proposals to undertake evaluation of the overall effectiveness of the scheme? | E8 | Requirements Fully Met | Yes, these are set out in the Monitoring and Evaluation Plan.

## Economic Case
INDEPENDENT REVIEW
Project Title: |  |  | MDC Validation Centre of Excellence
Permission Sought: |  |  | Full Approval |  | Date of Review: | 2020-11-15
ECONOMIC CASE
Overall Score |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  | The Economic Case falls short of full Green Book compliance in terms of both the option appraisal and the extent of the impact assessment. However, there is sufficient detail to demonstrate genuine consideration of alternative options and to evidence value for money within an acceptable BCR range. The argument that the forecast impacts are a likely understimation does have some merit and partly mitigates the lack of optimism bias in the BCR calculations. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[6 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[6 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Key relevant sections in Business Case | FBC Status | Comments
E1 | Has a Value for Money Statement been provided, including a BCR? | C3 | Requirements Fully Met | Yes, a value for money statement is included with a BCR of 2.04.
Benefits
E2 | Is the basis for the calculation of the Present Value of Benefits (PVB) sufficiently robust? Has sufficient information been provided on how this has been derived? | C1 | Requirements Fully Met | It is clear that the economic appraisal has been somewhat constrained by the limited evidence base for the sector. However, based on the data provided the PVB calculations have been done using Social Time Preference Rate for discounting and appear in this respect to be robust.
E3 | Is the basis for the calculation of the Present Value of Cost (PVC) sufficiently robust? Has sufficient information been provided on how this has been derived? | C1 | Requirements Fully Met | Yes, as above. The PVC relates only to the LEP grant income as all other costs are met by MDC directly or through income generated by the project.
E4 | Has an appropriate level of optimism bias been applied? | C1 | Requirements Partially Met | Optimism bias has not been included. However, the application notes the exclusion of several kinds of benefits due to the difficulty in providing accurate estimates. As a result, it makes the case that the forecast benefits are likely an underestimation. This is a credible assertion and may partly mitigate the lack of optimism bias.It should be noted that optimism bias would reduce the BCR to a value below 2, which is the LEP's usual (although not absolute) threshold for support.
E5 | Has an appropriate level of risk cost been included? | C1 and D1 | Requirements Fully Met | There is suitable contingency within the capital estimates and headroom in the operating model cashflow.
E6 | Have all relevant options been modelled / appraised? | C4 | Requirements Partially Met | As noted earlier, the option appraisal is limited when viewed against strict Green Book guidelines. However, a proportional approach is justified given the relatively low value of the investment.
Scheme Impacts
E7 | Has sufficient justification been provided on scoping out of any specific impacts? | C1 | Requirements Substantially Met | The economic appraisal provides a clear account of how impacts have been estimated and appears to have taken a reasonable and conservative approach. As noted, some possible impacts have not been estimated but they have been described in qualitative terms. In particular, it is difficult to estimate the potential uplift in the performance and value of firms using the Centre. This is due to the often long term nature of innovation and product development in this sector, and the dominance of IP-based business models. However, it is certainly reasonable to assume that some uplift would occur and the exclusion of this significant area of impact from the modelling underlines the conservative approach taken. Relevant evidence has been used where available, but this is somewhat limited. It is therefore difficult to appraise in detail the robustness of some of the estimates.
E8 | Has sufficient justification been provided on the approach used to appraise each impact (e.g. quantitative / qualitative)? | C1 | Requirements Fully Met | Yes, the narrative in C1 is clear and robust
E9 | Have all (relevant) Economic Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | C1 | Requirements Partially Met | There are no seven point scale ratings, and the application form does not appear to request this. However, the coverage of economic impacts does appear comprehensive even if supporting evidence is not always available.
E10 | Are forecast housing, jobs and GVA impacts provided robust / realistic? |  | Not Applicable
E11 | Have all (relevant) Environmental Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | C2 and G1-G5 | Requirements Substantially Met | There are no seven point scales and the form does not appear to request this. The project is not forecasting significant environmental benefits as this is not its purpose. However, there is good coverage of the measures that will be taken to ensure that the project is delivered in a way that is as environmentally sustainable as possible.
E12 | Have key environmental constraints been clearly identified? |  | Not Applicable
E13 | Have all (relevant) Social Impacts been adequately assessed? and are the ratings (seven-point scale) reasonable? | C2 and G6-G8 | Requirements Fully Met | There are no seven point ratings scales and the form does not appear to request this. There is a clear description of social benefits including health and public health benefis arising from the work of the project. There is also good coverage of the ways in which the project will support inclusive growth and equal opportunities within Section G.

## Financial Case
INDEPENDENT REVIEW
Project Title: |  |  | MDC Validation Centre of Excellence
Permission Sought: |  |  | Full Approval |  | Date of Review:
FINANCIAL CASE
Overall Score |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  | All main elements are covered, but would benefit from more detail regarding third party contributions, and financial risks (even if these do appear manageable). |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[6 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[6 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Key relevant sections in Business Case | FBC Status | Comments
F1 | Is the expected whole life cost of the scheme robust, including the base cost and risk allowance in out-turn prices drawn from industry forecasts? | D1 | Requirements Fully Met | Yes the cost estimates seem robust, but are not yet finalised - final costs are expected by March 2021
F2 | Has a cost profile been provided showing year on year costs, and breakdown by cost type and parties on whom they fall? | D1 | Requirements Fully Met | Yes, a full cashflow has been provided
F3 | Have details of key financial risks been provided and is the risk cost allowance robust? | E7 | Requirements Substantially Met | Financial risks are addressed in the Management Case section, and include cost overruns in the capital works. There is less clear treatment of ongoing financial risks that would arise if demand for the facility falls short of expectation, operational costs increase or income falls short. However, there is some headroom in the operational budget so these risks may not be major. They are also risks to MDC as the LEP has no ongoing financial commitment beyond the capital phase.
F4 | Are funding sources to cover the full scheme cost clearly set out? | F1 and F2 | Requirements Fully Met | Yes, this is clear.
F5 | Is there sufficient evidence to support third party / alternative funding contributions? | D2 | Requirements Partially Met | The only third party contribution is in-kind support for fit out from Alderley Park Limited and this should be confirmed.
F6 | Have the impacts of third party / alternative funding not coming forward been considered? | D2 | Requirements Partially Met | The project will not proceed without LEP funding, but the impact of the in kind support from Alderley Park not materialising is not made clear. This should be clarified along with suitable contingency plans, and should be recognised within the Project Risk Register.
F7 | Has the the long-term financial sustainability of the scheme been demonstrated, including robust plans to ensure the affordability of any ongoing costs for operation, maintenance? | D1 | Requirements Fully Met | Yes, the cashflow demonstrates that the facility can operate at a level that generates a surplus, which will be reinvested into MDC services. There is sufficient headroom in the financial model to manage some shortfall in income (approximately 10%-20%) and remain sustainable.
F8 | Has evidence of appropriate S151 Officer sign-off been provided? |  | Not Applicable