## Slide 1: Action Plan for Recovery and Growth
Purpose
The purpose of this action plan is to set out at high level the priority short term actions for the LEP for the period to January 2021. It is a pragmatic approach that aims to make early progress on delivering the vision to make Cheshire and Warrington the UK’s ‘most healthy, sustainable, inclusive and growing economy’. These short term actions will also form part of the wider Plan for Recovery and Growth which is currently being developed covering the medium-long term.
Objectives
Over the short term (12months): to achieve a reduction from the peak levels of unemployment resulting from the Coronavirus pandemic; ensure key decisions taken that advance our strategic priorities
Over the medium term (to 2023/24): to achieve a significant recovery in the employment market (comparable to pre-Covid levels) and demonstrable progress being made on the ground on key projects in the recovery action plan and wider plan for recovery, productivity, and growth.

## Slide 2: Powerful Partnerships to Build a Better Future Making Cheshire and Warrington the UK’s Healthiest, Most Sustainable, Inclusive and Growing Economy
Healthy (H) | Sustainable (S) | Inclusive (I) | Growing (G)
We will deliver locally on the government’s healthy ageing mission to ‘achieve an additional five years of healthy, independent life by 2035, while narrowing the gap between the experience of the richest and poorest’ | We will demonstrate leadership on sustainable growth. We recognise the value of our natural environment and will work to ensure that whilst securing sustained growth the environmental benefits of our activities outweigh the costs. | Cheshire and Warrington will be a place where people, regardless of their background or circumstances, are helped to ‘live their best lives’ | We will be the UK’s fastest growing economy, making the most of new opportunities inside and outside of the EU, driven by innovation and a top location for people and business to live, work, invest and relax
Halve levels of inactivity by 2030 Achieve scores of >8 and increasing on the ONS Population Survey Personal Wellbeing measure of Life Satisfaction Achieve scores below the England Mean (12.51%) for estimated prevalence of mental heath disorders Reduce the difference in life expectancy at birth between most and least deprived by 50% by 2035 | Reduce our Carbon Footprint by at least 2.5MtCO2 per year through development of a Net Zero industrial cluster in Ellesmere Port by 2030 Net Zero economy by 2050 Sustainability Commission established in 2020 Double use of sustainable transport and walking by 2025 [Measure linked to increasing bio-diversity and reducing resource use – awaiting baseline from Natural Capital Audit] | Eliminate in work poverty by 2030 Halve the number earning below the real living wage by 2025 ↑ % workers and residents engaged in learning ↓ % residents experiencing digital exclusion Strengthen our talent pipeline to ensure equality of opportunity for women and girls and our BAME and LBGTQ+ communities | Double size of economy by 2040 Employment and economic activity levels above 2019 rates by 2025 GDP per hr growing c.f. rest of UK Combination of public and private sector R&D spend >3% of our GDP, with Cheshire and Warrington participating fully in relevant national programmes.
Notes: So this is our current thinking on what that long term vision looks like tangibly – hwo we’d measure what success is. The vision is launched by leaders next week.

## Slide 3
PRIORITY ACTIONS | Review ESIF projects caught in approvals process H¦S¦I¦G | Produce draft Plan for Recovery & Growth H¦S¦I¦G | Finalise priorities for Plan for Recovery & Growth H¦S¦I¦G | Establish options in response to Recovery and Devolution White Paper H¦S¦I¦G | Work with NW Hydrogen Alliance on proposals for Hydrogen Catalyst S¦G | Place Marketing Strategy first phase development completed H¦S¦I¦G
 | Develop Action Plan for Retail, Hospitality & Visitor Economy H¦S¦I¦G | Finalise Cheshire Science Corridor EZ £30m borrowing facility S¦G | Establish and launch sub-regional Sustainable & Inclusive Growth Commission H¦S¦I¦G | Develop framework for sector recovery and preparation plans S¦I¦G | Work with Net Zero NW and NP11 on responses to Energy White Paper S¦I¦G | 
 | Set up access to Coursera Learning Platform I | Identify shovel ready projects for recovery in addition to £15m committed S¦G | Proposals on how ESIF could be repurposed to support recovery H¦S¦I¦G | Finalise Freeports proposition (joint with LCR / GM) G | Launch programme to develop key sector recovery and preparation plans. S¦I¦G | 
 | Develop and implement programme of online jobs and careers events I | Support HS2 Growth Corridor Business Case development (for submission September) G | CSR submission – including case for High Speed Growth Corridor H¦S¦I¦G | Support and input to LEP Network EZ Extension proposals G | Agree proposals with DIT and GM for Life Sciences HPO centred on Alderley Park / GM Health Cluster H¦G | 
 | Establish Workforce Recovery Group H¦S¦I¦G | Promote LEP business grants via Growth Hub and Marketing Cheshire I¦S¦G | Identification of potential short term growth / job creation opportunities. I¦G | Complete work to develop a costed Digital Infrastructure Plan S¦I¦G | Launch of enhanced account management programme for high growth companies S¦G | 
DIARY MARKERS | July | August | September | October | November | December
 |  |  | Party conference season LEP AGM | Energy White Paper? Freeports Comp Launch? Devo & Recovery White Paper |  | Budget / CSR End of Brexit Transition Period

## Slide 4
PRIORITY ACTIONS | Promote Accelerate training scheme for businesses I¦G | Develop outline Plan for Culture & Creative H¦SI¦I¦G | Launch ‘September Guarantee’ for Year 13 students in Chester & Ellesmere Port I | Finalise approvals etc for Getting Building Programme projects S¦I¦G |  | 
 |  |  | Planning for end of EU Exit Transition Period G | Review support for start ups I¦G |  | 
 |  |  |  | Finalise Life Sciences Fund 2 H¦G |  | 
 |  |  |  | Develop an Export Strategy G |  | 
DIARY MARKERS | July | August | September | October | November | December
 |  |  | Party conference season LEP AGM | Energy White Paper? Freeports Comp Launch? Devo & Recovery White Paper |  | Budget / CSR End of Brexit Transition Period

## Slide 5
PRIORITY MESSAGES | Promote reopening. 'Simple pleasures' and 'Your Cheshire' campaigns | Scale up regional visitor economy messages | Joint statement on vision for economic recovery | Press and paid-for advertising on visitor economy? | Cheshire and Warrington – UK centre for clean and sustainable growth | Visitor economy and independent business messages for Christmas
 | Promoting inclusion through Computers for Schools. | Engaging business on a plan for recovery, jobs and growth | Launch new schemes - £15.5m investment from HMG | Healthy – LEP promotion of winter flu jabs? | Supporting business through recovery and post-transition | 
 |  |  | ‘September Guarantee’ – Chester & Ellesmere Port | Cheshire and Warrington – Open for Investment |  | 
 |  |  | CSR Submission |  |  | 
POLICY MARKERS | July | August | September | October | November | December
 |  |  | Party conference season LEP AGM | Energy White Paper? Freeports Comp Launch? Devo & Recovery White Paper |  | Budget / CSR End of Brexit Transition Period

## Slide 6: July
Item | Activity Required | By Whom | Comment
Review ESIF projects caught in the approvals process | Review those projects identified as priorities for the Cheshire and Warrington ESIF programme which have been successfully through initial gateway stages and ESIF Committee approval but which are still awaiting final sign off from DWP or others. | CWLEP (Pat Jackson / Tim Smith) | Gap analysis undertaken to inform thinking on potential additional calls for projects using national reserve funds.
Develop Action Plan for Retail, Hospitality and Visitor Economy | Development of a new Destination Management Plan for Cheshire and Warrington including responding to government calls for proposals on Tourism Action Zones Framework for support hospitality and tourism businesses throughout the autumn and winter with destination campaigns integrated into national activity delivered by Visitbritain Collaboration with BIDs and town centres across Cheshire and Warrington to further support high street reopening and high street place development as part of Town Deal proposals | Marketing Cheshire | Underway
Develop and implement programme of online jobs and careers events | Confirm programme and operational requirements for minimum five online jobs fairs in conjunction with JCP plus programme of events led by the Pledge to support young people in career and education choices | CWLEP / JCP? | COMPLETED. First jobs fair held for Crewe and Nantwich area in August. Programme now planned through to January 2021.
Establish Workforce Recovery Group | LEP to lead on establishing a multi-agency Workforce Recovery Group. The Group will be tasked with developing a programme of support for workers impacted either through furlough or redundancy. This will include identifying potential gaps in provision. |  | COMPLETED

## Slide 7: July
Item | Activity Required | By Whom | Comment
Promote Accelerate training scheme to businesses | Marketing and comms plan to be produced and signed off and start of associated marketing and comms activity | CWLEP / University of Chester | ONGOING
Set up access to Coursera learning platform | Sign sub-region up to initial six-month offer of free training for recently made redundant / furloughed workers | CWLEP | COMPLETED

## Slide 8: August
Item | Description / Activity Required | By Whom | Comment
Produce Draft Plan for Recovery and Growth | Current work stream output to be pulled together into a single draft document using an agreed structure, for consultation. Includes focus on short term jobs growth. | CWLEP (Andy Hulme) | Links to CSR submission and to Investment Pipeline activity
Identify shovel ready projects for recovery in addition to the £15.5m Getting Building Fund projects | Review of the current LEP investment pipeline to ascertain which projects could be accelerated / start on site within the next six months, which would generate jobs and support wider economic recovery. | CWLEP (Roy Newton) | 
Develop outline plan for Culture and Creative | Legacy commitment from LEP Quality of Place Strategy. The plan is to rescope and integrate into the recovery programme and as a key strand of place-marketing. Creative and culture sectors have a lot to add to LEP’s vision – particularly on sustainable, inclusive and healthy. Outline developed August / September with a view to starting / commissioning activity in October. | Marketing Cheshire / CWLEP | 
Finalise Cheshire Science Corridor EZ £30m EZ borrowing facility |  | CWLEP / Local Authorities (Ian Brooks / John Adlen) | 
Promote LEP Business grants via Growth Hub and Marketing Cheshire | Develop process for allocating initial £500k of LEP support grants for business; launch and promote the scheme | CWLEP / Marketing Cheshire | Already oversubscribed.
Supporting a High Speed Rail Growth Corridor Business Case submission | Support Cheshire East and other partners to develop a detailed business case to be completed and submitted to DfT / MHCLG (?) for consideration alongside the Comprehensive Spending Review . | CWLEP (Roy Newton /John Adlen) | Rebranding as High Speed Rail Growth Corridor and expanded to include Warrington / Northern Powerhouse Rail

## Slide 9: September
Item | Description / Activity Required | By Whom | Comment
Finalise priorities for the Plan for Recovery and Growth | Reflect feedback from virtual roundtables / stakeholder engagement to produce a final draft of the plan to coincide with the LEP AGM at the end of September | CWLEP (Andy Hulme) | Key messages also to be used as core submission to CSR call for representations.
Roll out work programme developed by the Workforce Recovery Group. | Comprehensive plan developed by the group. Roll out of workstreams to start in September. Five workstreams in total plus marketing and communications | CWLEP / Marketing Cheshire (Andy Farrall / Pat Jackson) | 
Identify priority projects for short-medium term growth |  | CWLEP (Roy Newton) | Links to Recovery and Growth Plan and CSR submission
Establish and launch sub-regional Sustainable and Inclusive Growth Commission | Finalise Terms of Reference and outline plan of activity. Confirm identity of joint Chairs and launch as part of confirmation of post-Covid vision for Cheshire and Warrington | CWLEP and Local Authorities | 
Planning for end of EU Exit Transition Period | Developing plan for engaging and supporting business to prepare for the end of the EU Exit Transition period on 31st December 2020. | Growth Hub | Likely to include an element of local delivery of national activity
Set out proposals for how remaining ESIF monies could be repurposed to support recovery | Opportunity to request DWP to issue a number of further calls for projects to utilise remaining ESF funding. Review how this could be done in a way which is aligned to Covid recovery and scope out potential programmes for consideration | CWLEP | May require outline of the Recovery Plan to be ready to support any request of DWP

## Slide 10: September
Item | Description / Activity Required | By Whom | Comment
Launch “September Guarantee” for Year 13 students in Chester and Ellesmere Port | Local programme part-funded by the Westminster Foundation. Actitivty led by Youth Federation and supported by the Pledge. | Youth Federation / The Pledge | Youth Fed currently working on bid to other national funding pots to develop a sub-region-wide offer
Finalise and submit a response to the call for representations on the Comprehensive Spending Review (24/9) | Draft response to be prepared for discussion by early September. Aligning submission with sub-regional priorities including activities and projects identified in the recovery plan. | CWLEP / Local Authorities (?) | Need to confirm if this is a joint response or if LAs plan to submit individual responses.
Identification of potential short term growth / job creation opportunities. | Work with Local Authorities to identify companies in the existing business base that are looking to expand / bring forwards investment plans, with a view to stimulating job creation. | CWLEP / Local Authorities | 

## Slide 11: October
Item | Description / Activity Required | By Whom | Comment
Establish options in response to Recovery and Devolution White Paper | White Paper and supporting consultation on Recovery and Devolution is expected to be published in the early autumn (date still tbc). LEP to support and engage in discussions at a sub-regional level to establish options in terms of response. To be scoped following further discussion with SRMB / SRLB | LEP (Philip Cox) | Note – lack of certainty on date for publication and scope of the White Paper.
Develop agreed position / proposition for a Freeport, potentially as a joint proposal with LCR and GMCA, in preparation for launch of a Freeports competition | Discussions initially to identify appetite for joint proposal anchored around the Port of Liverpool but incorporating a number of manufacturing-related sites in C&W, principally along the Manchester Ship Canal. |  | Conversations with LCR and GM on a joint proposal currently being supported by NWBLT.
Complete work to develop a costed Digital Infrastructure Plan for Cheshire and Warrington | Consultants appointed and currently on track to finalise report and recommendations in late September / early October. | CWLEP | 
Support and input to the LEP Network activity to develop proposals for an extension to the Enterprise Zone programme |  | CWLEP (John Adlen / Ian Brooks) | Potential for separate activity to develop proposal to extend life of CSC EZ

## Slide 12: October
Item | Description / Activity Required | By Whom | Comment
Finalise details for GM and Cheshire Life Sciences Fund II | Complete outline business case for CWLEP LGF application | CWLEP / GM / Bruntwood | 
Finalise approvals for projects being funded through the Getting Building Fund | Ensure business cases are available for approval by the LEP’s Performance and Investment Committee so that Offer Letters can be issued and funding confirmed. | CWLEP | 
Develop framework for sector recovery and preparation plans [and launch of Peer-2-Peer support programme??] | Developing details for working with businesses and business representative organisations across our key sectors (including key enabling sectors) to create high level of action to support recovery, growth and also prepare for the UK’s new trading arrangements post-Transition period. Links to Peer-2-Peer support programme | CWLEP / Growth Hub | Life Science Manufacturing Logistics Energy & Clean Growth Chemicals Agriculture, Food and Beverage Finance & Business Services Culture & Creative
Develop an Export Strategy | Funding secured from DIT to develop a Cheshire and Warrington Export Strategy. Work to be commissioned for completion by March 2021. | CWLEP / Growth Hub | 
Review support for start ups | Review and where possible refocus existing Growth Hub provision to offer more targeted support and mentoring for high potential start ups | CWLEP / Growth Hub | 

## Slide 13: November
Item | Description / Activity Required | By Whom | Comment
Work with NP11 and others to develop appropriate responses to the Energy White Paper (assuming this is launched in October 2020). | Working assumption that the NP11 Low Carbon Group will develop and submit a response to the Energy White paper. CWLEP to input to ensure that the particular strengths of Cheshire and Warrington are reflected as part of the wider northern offer | CWLEP | Potentially separate C&W response also.
Develop local proposals for creation of a Hydrogen Catalyst | TBA | CWLEP / Net Zero North West / University of Chester? | 
Launch programme to develop key sector recovery and preparation plans. | Work with sector representative organisations (e.g. Northern Automotive Alliance, Chemicals North West, Make UK, BioNow) and businesses in our key and supporting sectors to develop practical plans for how they will continue to recover post-Covid-19, growth and also prepare for the new trading relationships with the world post-31st December 2020. | CWLEP / Growth Hub / Marketing Cheshire | QUESTION – This feels like it might be too late in the programme – October might be better in terms of launch?
Agree proposals with DIT and GM for Life Sciences HPO centred on Alderley Park / GM Health Cluster | Follow up on current conversations with Alderely Park and GM to respond to DIT invitation to develop a HPO for Life Sciences focussed on that geography. | CWLEP / GM / DIT / Alderley Park Ltd | 
Launch of enhanced account management programme for high growth companies | Enhanced account management programme for an identified cohort of higher growth businesses focussed on key sectors. Will include peer-2-peer support and link to the sector recovery and preparation plans | CWLEP / Growth Hub (Andy Devaney) | 

## Slide 14: December
Item | Description / Activity Required | By Whom | Comment
Complete first phase development of Cheshire and Warrington Place Marketing Strategy | Build on work undertaken with Regeneris and UpThereEverywhere to develop a place identity and marketing strategy for Cheshire and Warrington. Clarify any further work that needs to be commissioned and proposals for further stakeholder engagement in 2021 ahead of launching strategy. | CWLEP / Marketing Cheshire | 

## Slide 15
PRIORITY ACTIONS | Jan - Implement programme of support for business if required following the end of the EU-Exit Transition Period |  |  | 
DIARY MARKERS | Q1 2021 (Jan – Mar) | Q2 2021 (Apr – Jun) | Q3 2021 (Jul – Sep) | Q4 2021 (Oct – Dec)
 | Start of new trading relationships post EU Exit (1/1/21) |  |  | 

## Slide 16
PRIORITY MESSAGES | Jan - Cheshire and Warrington on global stage – launch of inward investment programme |  |  | 
POLICY MARKERS | Q1 2021 (Jan – Mar) | Q2 2021 (Apr – Jun) | Q3 2021 (Jul – Sep) | Q4 2021 (Oct – Dec)
 | Start of new trading relationships post EU Exit (1/1/21) |  |  | 

## Slide 17: January 2021
IItem | Description / Activity Required | By Whom | Comment
Roll out of programme of support (if required) following end of EU-Exit Transition Period | Potential support to be identified in advance of 1st January 2021 in the event that the Transition Period ends without appropriate trade agreements in place to minimise disruption to business and markets. | CWLEP / Growth Hub | Programme of support may be required in any event in order to help business understand and navigate new trading arrangements with the EU and other countries from 1st January 2021.